## Sprint1 FIX
Project: BFH Server: dertobi.visualstudio.com\derTobi Query: Team Green - Iteration 1 - Backlog List type: Tree
ID | Work Item Type | Title 1 | Title 2 | State | Iteration Path | Assigned To | Remaining Work | Original Estimate | Estimate Updated
13 | User Story | Infrastruktur |  | New | \Sprint 1
14 | Task |  | Basislayout erstellen | Closed | \Sprint 1 | Joris |  | 8 | 10
17 | Task |  | Navigation erstellen | Active | \Sprint 1 | Lukas Läderach | 6 | 8 | 10
15 | Task |  | Erstelle Datenbankstruktur | Closed | \Sprint 1 | Cedric von Allmen |  | 5 | 5
18 | Task |  | Configure OR-Mapper | Closed | \Sprint 1 | Cedric von Allmen |  | 2 | 8
16 | Task |  | Seed Daten | Active | \Sprint 1 | Tobias Joder | 1 | 2 | 2
19 | Task |  | Use a more smart object to object mapper like Automapper | New | \Sprint 1 |  |  | 3 | 3
33 | Task |  | Install und Config MySql (+Local) | Closed | \Sprint 1 |  |  | 3 | 3
35 | Task |  | Know-How transfer | Closed | \Sprint 1 | Tobias Joder |  | 6 | 6
12 | User Story | Suche |  | New | \Sprint 1
20 | Task |  | Searchbox auf UI-Header | Closed | \Sprint 1 | Simon Schmid |  | 2 | 2
21 | Task |  | Suchservice(s) | Active | \Sprint 1 | Tobias Joder | 3 | 4 | 4
22 | Task |  | Model | Active | \Sprint 1 | Tobias Joder | 1 | 2 | 2
23 | Task |  | Resultview | Active | \Sprint 1 | Tobias Joder | 4 | 4 | 4
24 | Task |  | Presenter | Active | \Sprint 1 | Tobias Joder | 1 | 2 | 2
2 | User Story | Journal |  | New | \Sprint 1
25 | Task |  | Journalservice | Active | \Sprint 1 | Tobias Joder | 2 | 2 | 2
26 | Task |  | Journal Übersicht (View) | Active | \Sprint 1 | Tobias Joder | 4 | 4 | 4
27 | Task |  | Journalpresenter | Active | \Sprint 1 | Tobias Joder | 2 | 2 | 2
28 | Task |  | Model | Active | \Sprint 1 | Tobias Joder | 3 | 3 | 3
30 | Task |  | View in Mainview einbinden | Active | \Sprint 1 | Tobias Joder | 1 | 1 | 1
Mitglieder | 6 | [5 empty] | 27 | 63 | 73 | h erfasst
Stunden Soll | 7 |  |  | Work Done | (Estimated - Remaining) | 46 |  | -21 | -31 | Kapazität
Kapazität Theoretisch = 42