## Sprint 3
Project: BFH Server: dertobi.visualstudio.com\derTobi Query: Team Green - Iteration 3 - Backlog List type: Tree
ID | Work Item Type | Title 1 | Title 2 | State | Iteration Path | Assigned To | Remaining Work | Original Estimate | Original Estimated | Original Updated
54 | User Story | Journal Editable |  | Closed | \Sprint 3 | Tobias Joder | 0
65 | Task |  | CUD | Closed | \Sprint 3 | Tobias Joder | 0 | 5 | 5 | 7
55 | User Story | Authentication |  | Closed | \Sprint 3 | Lukas Läderach | 0
63 | Task |  | O-Auth | Closed | \Sprint 3 | Lukas Läderach | 0 |  | 4 | 5
64 | Task |  | Rolle(n) | Closed | \Sprint 3 | Lukas Läderach | 0 |  | 1 | 1
56 | User Story | Cleanup Code |  | Closed | \Sprint 3 |  | 0
57 | Task |  | Lüku | Closed | \Sprint 3 | Lukas Läderach | 0 |  | 5 | 5
58 | Task |  | Cedric | Closed | \Sprint 3 | Cedric von Allmen | 0 |  | 5 | 5
59 | Task |  | Joris | Closed | \Sprint 3 | Joris | 0 |  | 5 | 5
60 | Task |  | Mathew | Closed | \Sprint 3 | Mathew Thekkekara | 0 |  | 5 | 5
61 | Task |  | Simu | Closed | \Sprint 3 | Simon Schmid | 0 |  | 5 | 5
62 | Task |  | Tobi | Closed | \Sprint 3 | Tobias Joder | 0 |  | 5 | 5
31 | User Story | MockUps Umsetzung |  | Closed | \Sprint 3 | Tobias Joder | 0
66 | Task |  | AppointmentDetailView | Closed | \Sprint 3 | Cedric von Allmen | 0 |  | 5 | 6
67 | Task |  | PatientDetailView | Closed | \Sprint 3 | Mathew Thekkekara | 0 |  | 5 | 6
69 | Task |  | Appointment CRUD | Closed | \Sprint 3 | Simon Schmid | 0 |  | 5 | 6
70 | Task |  | Stylerei | Closed | \Sprint 3 | Joris | 0 |  | 1 | 1
71 | Task |  | MyDay | Closed | \Sprint 3 | Joris | 0 | 2 | 2 | 3
72 | Task |  | PatientsOverview | Closed | \Sprint 3 | Joris | 0 | 2 | 1 | 2
73 | Task |  | Appointment State Improvement | Closed | \Sprint 3 | Simon Schmid | 0 | 3 | 3 | 4
74 | Bug |  | Fix Unit Test for Appointment UI | Closed | \Sprint 3 | Simon Schmid | 0 | 1 | 1 | 2
75 | User Story | AlarmButton |  | Closed | \Sprint 3 | Joris | 0 | 5 | 5 | 3
76 | Task |  | Button im UI einfügen | Closed | \Sprint 3 | Joris | 0 |  | 1 | 0.5
Mitglieder | 6 | [5 empty] | 0 |  | 69 | 76.5 | h erfasst
Stunden Soll | 9 |  |  | Work Done | (Estimated - Remaining) | 76.5 |  |  | -15 | -22.5 | Kapazität
Kapazität Theoretisch = 54